## Agile Plan
Sprint | Start Date | End Date | Tasks | Assignee 1 | Assignee 2 | Completed
0(Pre-Planning) | 2017-07-12 | 2017-07-16 | Choose team member roles | All | - | Done
|  |  | Choose project | All | - | Done
|  |  | Choose technology | All | - | Done
|  |  | Plan next sprint | All | - | Done
|  |  | Prepare project description document | Vanipenta, Manoj Kumar (m_v219) | Kidambi Sekar, Aarthy (a_k196) | Done
1 | 2017-07-17 | 2017-07-24 | SRS preparation | Umbarkar, Reena (r_u22) | - | Done
|  |  | GitHub setup | Kidambi Sekar, Aarthy (a_k196) | - | Done
|  |  | Development environment setup | All | - | Done
|  |  | Class diagram / Code skeleton | Kidambi Sekar, Aarthy (a_k196) | - | Done
|  |  | Basic UI | Kidambi Sekar, Aarthy (a_k196) | - | Done
|  |  | Create/Load Puzzle | Kidambi Sekar, Aarthy (a_k196) | - | Done
|  |  | Swap tiles | Kidambi Sekar, Aarthy (a_k196) | - | Done
2 | 2017-07-25 | 2017-08-01 | Acceptance Test plan / Test Estimation | Vanipenta, Manoj Kumar (m_v219) | - | Done
|  |  | Integration Test plan | Zhou, Pingheng (p_z12) | - | Done
|  |  | Documentation preparation | Umbarkar, Reena (r_u22) | - | In-Progress
|  |  | New puzzle | Kidambi Sekar, Aarthy (a_k196) | - | Done
|  |  | Login | Kidambi Sekar, Aarthy (a_k196) | - | Done
|  |  | Unit test | Kidambi Sekar, Aarthy (a_k196) | - | In-Progress
|  |  | Integration Test cases | Zhou, Pingheng (p_z12) | - | In-Progress
|  |  | Acceptance Test cases | Vanipenta, Manoj Kumar (m_v219) | - | Done
3 | 2017-08-02 | 2017-08-08 | Unit test | Kidambi Sekar, Aarthy (a_k196) | - | To Do
|  |  | Final Documentation preparation | Umbarkar, Reena (r_u22) | - | To Do
|  |  | Acceptance Testing | Vanipenta, Manoj Kumar (m_v219) | - | To Do
|  |  | Save puzzle | Kidambi Sekar, Aarthy (a_k196) | - | To Do
|  |  | Solve puzzle | Kidambi Sekar, Aarthy (a_k196) | - | To Do

## Team members
Kidambi Sekar, Aarthy (a_k196)
Umbarkar, Reena (r_u22)
Vanipenta, Manoj Kumar (m_v219)
Zhou, Pingheng (p_z12)
All